## Sheet1
|  | Roman: 0.9.0 win 64-bit (2016-03-15), Windows 7 64-bit, Java jdk1.8.0_74 64-bit with ConfModel |  |  | Roman: 0.9.0 win 64-bit (2016-03-17), Windows 7 64-bit, Java jdk1.8.0_74 64-bit with QM model
Scenario Nr | Name | Result | Comment | Actions | Result | Comment | Actions
1 | Log in (initial model download) | pass |  |  | pass
2 | Start using local data (no log in required) | pass |  |  | pass
3 | Saving changes in the local model | pass |  |  | pass
4 | Switching between no login (local data) to login(repository connection) | pass |  |  | pass
5 | Saving by using CTRL+S and Model¦Save All | pass |  |  | pass
6 | Selecting an Artifact | pass |  |  | pass
7 | Selecting an Artifact (Pipeline Editor) | fail | … button does not appear |  | pass
8 | Reverting all changes | pass |  |  | pass
9 | Adding a new Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass |  |  | pass
10 | Configuring a new Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass | GP machine is placed in subgroup but the original stays in the top-level. Gone after app restart. |  | pass | GP machine is placed in subgroup but the original stays in the top-level. Gone after app restart.
11 | Configuring a new Algorithm, Source or Sink via Manifests | pass | filled only after class selection (not just algorithm) | Change in the description | pass | Only Algorithm tested
12 | Editing a Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass |  |  | pass
13 | Deleting a Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass | deleting MPCCNode did not update the editor. After deleting did not work on other elements. Wored after app restart. |  | pass
14 | Cloning a Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, Algorithm | pass |  |  | pass
15 | Copying input/output fields | pass |  |  | pass
16 | Adding a pipeline | pass |  |  | pass
17 | Deleting a pipeline | pass |  |  | pass
18 | Using the Graphical Pipeline Editor | pass
19 | Defining / changing constraints | fail | unable to add (OK button inactive) |  | fail | DM constraints are added and removed. For pipeline constraints: constraints are added and shown in the property view. But upon pressin … to access them an empty window opens (so nothing to edit). After restarting model is broken.
20 | Help texts for configuration entries | pass |  |  | pass
21 | Help texts for configuration sections | pass |  |  | pass
22 | Help documentation | fail |  |  | pass
23 | Validating the model | pass |  |  | pass
23--1 | Worker Machine has no ports assigned | pass | ConfModel needs to be updated. Results based on QM model.
23--2 | Input/output mismatch in Algorithm Families and Algorithms | pass | ConfModel needs to be updated. Results based on QM model.
23--3 | Input/output mismatch by an additional Flow | pass | ConfModel needs to be updated. Results based on QM model.
23--4 | Input/output mismatch by an additional element and two flows | pass | ConfModel needs to be updated. Results based on QM model.
23--5 | Input/output mismatch with Data Management Element | pass | ConfModel needs to be updated. Results based on QM model.
24 | Instantiating | pass