## Sheet1
|  | Roman: 0.8.5 win 64-bit (2016-01-11), Windows 7 64-bit, Java jdk1.8.0_66 64-bit |  |  | Roman: 0.8.5 win 64-bit (2016-01-12), Windows 7 64-bit, Java jdk1.8.0_66 64-bit
Scenario Nr | Name | Result | Comment | Actions | Result | Comment | Actions
1 | Log in (initial model download) | pass | new repository configuration window | -> test scenarios | pass
2 | Start using local data (no log in required) | pass |  |  | pass
3 | Saving changes in the local model | pass |  |  | pass
4 | Switching between no login (local data) to login(repository connection) | pass | new message; yes - local data saved, no - data from the repository restored | changed | pass
5 | Saving by using CTRL+S and Model¦Save All | pass |  |  | pass
6 | Selecting an Artifact | pass | Cancel instead of Close; when artifact selected in the file tree UI selection jumps to the nesting folder, might be confusing | -> test scenarios | pass
7 | Selecting an Artifact (Pipeline Editor) | fail | artifact can be selected but is not saved (editor is not set dirty) | file issue | pass/fail | Selection is possible, but the editor is not set dirty. As workaround make some other change and then it is possible to save.
8 | Reverting all changes | pass |  |  | pass
9 | Adding a new Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass |  |  | pass
10 | Configuring a new Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass | if machine name is set to "roman" then displayed as "ports" in the view; attribute fileds in the UI of a new added Data Management and Algorithms are smaller | file issue, see also issue #34 | pass | For GP Machines name in the view changes only after restarting app; attribute fileds in the UI of a new added Data Management and Algorithms are smaller;
11 | Editing a Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass |  |  | pass
12 | Deleting a Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, or Algorithm | pass |  |  | pass
13 | Cloning a Type, General-purpose Machine, Reconfigurable Hardware Machine, Data Management, Algorithm Family, Algorithm | pass |  |  | pass
14 | Copying input/output fields | pass | for algorithms not clear what to copy from data managemet elements (input of output); nothing can be copied from algorithms; | ok for now | pass | From sink only output, from source input; when copying it does not add but replaces all fields you already have;
15 | Adding a pipeline | pass |  |  | pass
16 | Deleting a pipeline | pass |  |  | pass
17 | Using the Graphical Pipeline Editor | pass |  |  | pass
18 | Defining / changing constraints | pass/fail | only for data management and pipeline elements; in pipelines only add and remove constraints, can not save, constraint not checked; |  | pass/fail | Algorithm Family do not have constraints in UI (changed document); in Pipeline Editor possible to add constraint for all elements(after adding click on the diagram space to set editor dirty); in Pipeline editorconstraints not check for syntax (name > 1 can be added)
19 | Help texts for configuration entries | pass |  |  | pass
20 | Help texts for configuration sections | pass |  |  | pass
21 | Validating the model | pass |  |  | pass
21--1 | No manager is assigned in Machines | pass | nimbus1.sse.local is also a manager so only 1 error found | -> test scenarios | pass
21--2 | Input/output mismatch in Algorithm Families and Algorithms | pass |  |  | pass
21--3 | Input/output mismatch between Family Elements | pass | in the editor elements stay maked red after error is fixed and validation was ok | see also issue #38 | pass
22 | Instantiating | pass |  |  | pass